## Sheet1
Date assigned | Task | Date Completed | Deadline | Type of Change | Notes
2019-05-31 | Import basic calculator function from earlier course work | 2019-05-31 | 2019-05-31 | Import/Add | Calculator functions are under calculator_base.py
2019-05-31 | Install necessary modules | 2019-06-01 | 2019-06-02 | Installation | Installed Equation and matplotlib
2019-05-31 | Create graphing calculator branch of calculator | 2019-06-05 | 2019-06-06
2019-06-01 | Implement plotting | 2019-06-02 | 2019-06-04 | Add | Still needs to be configured to graph desired functions Could not find way to graph discontinuous functions
2019-06-01 | Implement equations | 2019-06-02 | 2019-06-04 | Add
2019-06-01 | Add comments | 2019-06-08 | 2019-06-09 | Documentation